## Action plan
APPENDIX C1 - South Holland Industrial Heritage Marketing and Communications Strategy
| Action | Further detail | Implementation | Accountable person | Priority | Estimated costs
1 | Develop a PR & marketing calendar | Templates for calendar provided within this spreadsheet, see tabs at bottom. To give direction and focus for 5 years of collaborative marketing to attract new audiences and share costs. | All three teams to get together and complete the detail in the calendar to create a plan of action for promotions each year. Each year will have its own calendar and future planning will use this template as well. We have added in some recommended actions and timings, but these will need to be adapted according to resource. Also, the finer detail of activity relating to programming and events will need to be added when this plan is in place. | Geoff, Karen and Janet | Year one Detailed calendar should be in place before any delivery is considered. | Free. Time resource only
2 | Brand | Develop the new collaborative brand - to include visual identity, tone of voice, imagery. This will create a stronger identity or 'selling point' for the three sites, which will aid collaborative PR and Marketing opportunities. | We would recommend building this into the process of designing the website. Once an external company has been assigned they can work with you to discuss the spirit of place (what makes your site special, why, and what 'spirit' of the heritage asset you want to protect, conserve, and promote in future) of each site to develop a brand that works for the new collaboration. | Geoff, Karen and Janet | Year one To allow any of the marketing collateral to be created you will need the new brand to be in place. | To be built into the below/website design
3 | Design and build collective South Holland Industrial Heritage website | Bring all three properties together for more strategic and cost saving promotions, to allow for cross promotions to visitors and create an up-to-date and informative visitor experience online. | We have found a number of sites which we believe operate in a similar way to how the new collaborative site should work. https://www.ironbridge.org.uk/ https://www.derbymuseums.org/ www.museums-sheffield.org.uk http://www.aviationheritagelincolnshire.com An outline for a SHIH web map is included in Appendix C6 Initially a tender will need to be raised to source a suitable website designer. Once a company has been chosen you will work with them to create a site map and agree the design before implementation. We would recommend asking for a website with it's own content management system to allow you to update the content yourselves. | Geoff, Karen and Janet | Year one Once this plan is in place we recommend this to be the first marketing task to be completed as you need the content to refer all other forms of marketing and PR. | It is difficult to advise on an exact cost until we know the exact specification. We would recommend a minimum spend of £5k which will give you a basic site. If you need the site to capture data, include a content management system or any other additional systems you will need be looking at £10k - £15k.
4 | Build new collaborative Facebook & Twitter pages and create a social media plan | In line with the website, create one Facebook and one Twitter account to promote all three properties to enable broader reach and consistent digital communications. This will strengthen the brand, provide a better online visitor experience, and present a more cohesive identity for the three sites. | Assigning a volunteer with marketing experience would be our recommendation for completing this element of the strategy. Creation of both Facebook and Twitter pages is a self-explanatory process and shouldn't take a great deal of time. We then recommend communicating on the current social media accounts that your new pages are live, to encourage them to like this page and then delete the old pages/accounts. For Facebook this is best done through www.business.facebook.com so you can assign a number of administrators. We then recommend setting up a social media plan to ensure you are communicating to your followers on a regular and consistent basis and with relevant messages. Please see an example plan in 'social media plan' tab. Again, the finer details will need to be completed when the website is set up with content to link to and when you have a programming/events plan. | Janet/volunteer | Year one Creating new social accounts is relatively quick and once the plan is in place scheduling can begin. Years 2-5 and ongoing Work to deliver your social media schedule to communicate your stories, events and share news and imagery. | Free. Time resource only
5 | Digital advertising (PPC (pay per click), Facebook) | Re-direct and reduce spend from print advertising to digital advertising to allow for more targeted activity which can then be better evaluated. Pay per click gives presence on other websites through targeted banner adverts whilst Facebook advertising can offer very targeted conversational advertising to widen the visitor community. | Once your website is in place and you are in a position to communicate your collaborative working and new events/programming, we would recommend starting digital advertising to drive visits to the three sites. How this is delivered will depend on the resource available; a marketing volunteer might be able to deliver this, otherwise an external company might be best to be approached. | Karen | Year two Digital advertising needs to be well planned and targeted. Years 3-5 and ongoing Work to deliver a targeted and consistent digital advertising plan using evaluation from all activity to help determine the next. | The more you spend the greater audience reach you will achieve, but as a minimum we would recommend £50 per month or to consider 3-4 planned promotions per year with estimated £200 behind each promotion. We would also recommend focusing on Facebook advertising in the early days as PPC can be expensive, to make an impact you would need to consider a minimum of £250-£300 per month and this would probably be better spent on Facebook, you'll get more for your money.
6 | PR | Send out Press Releases to local media (see suggested media list) on: - Half-term/summer holiday events - News e.g. new sail going up on the windmill, an interesting commission completed by the forge Local history talks shared by the sites: - Moulton Mill talk about the woad industry - CBF blacksmithing/general local area - PEM on history of water management with involvement of the Drainage board? - Could be hosted at the windmill as part of a series of local history talks throughout the year, could invite other local attractions/experts to do talks as well, feed into social media and do Press Releases. Inviting BBC Radio Lincolnshire to visit all three sites for a general feature e.g. grind flour at the windmill, hammer a hook at the forge, switch on the engine at Pinchbeck etc… Use visit as a chance etc. promote e.g. summer holiday events so would be best done in the Spring - BBC Radio Lincolnshire has been suggested in particular here because each of these sites has a unique 'audio' offer which the station might be interested in and might therefore be a more successful approach than TV. A suggested contact would be Joanna Knight who we have worked with previously - joanna.knight@bbc.co.uk (see media list for full recommendations) | PR is a great way to engage with new audiences, especially when marketing resources are tight. However, if you are wanting to draw attention to yourselves you need to make sure that your 'welcome mats'/shop windows (website and social media platforms') are sorted first. Once your brand is set and your website and social channels are up and running with a comfortable following (more than 100 preferably), we would advice you engaging in some local/regional PR activity. We have provided a Press Release template and guidance document which you might want to consider when planning PR. PRs can be sent out to local media around good news stories, such as what's coming up over half-term/summer holidays, or conservation news such as the sail going back up on the mill, or to recruit volunteers. | Geoff, Karen and Janet One individual to co-ordinate and write press releases, distribute, and take media enquiry calls - volunteer? | Year One/Two Once website, social and on site marketing is improved so that new interested visitors are landing on a strong website/social media platforms and are more likely to visit | Free. Time resource only
7 | Collaborative leaflet | We suggest producing collaborative leaflet to replace the three individual site leaflets in order to share costs and form a cross-site marketing function. This would provide basic information; introducing each site, key visiting information, and website/social details. No events included to avoid requiring regular updates - 'see our website for upcoming events'. Only updated when necessary e.g. new prices/opening times etc. Option to distribute this leaflet to local cafes and businesses as well as tourist centre etc. | Again this needs to be completed after the website and social media platforms are established, so that the new website and social details can be included. Costs here are based on a collaborative NT leaflet called 'Be Curious'. This leaflet covered three smaller properties in the Midlands; The Birmingham Back to Backs, Mr Straw's House, and Stoneywell cottage. Bearing in mind the lower distribution and print costs, because you would not need to print as many leaflets, we have indicated the estimated costs provided. You may want to ask for a quote from this local printer, currently used by Belton - Printhub sales@printhub.co.uk Many of our properties in the Midlands use the designers 'Red Riot' for their print work. | Geoff, Karen and Janet | Year One Website first, again so new visitors land on a strong site. | Indicative costs, based on a similar NT collaborative leaflet: Quantity = 25k Print costs = £1k Distribution = £900 Design costs = £150
8 | On site table talkers | These would detail information on upcoming events at the three sites, and recent news e.g. conservation work or new sail at the mill etc. Website and social details provided. Preferably updated twice a year to keep information fresh and seasonal. Costs are based on the common production of table talkers at our sites. | When you approach a designer for the collaborative leaflet, you could ask them to put together a table talker template design, which you can then regularly update as/when appropriate but print on site to reduce costs of production. | One individual, probably at the Mill as the café is on-site, to co-ordinate - using details provided by the forge and PEM. Janet to determine | Year Two Get the website, social media and programme of activities sorted first so you know what to detail and include. | Quantity = 50 Design & print = £100 (indicative)
9 | Briefing to visit reception staff | Make sure reception staff/'front of house' volunteers are aware of the upcoming events/activities and news across all three sites so they cross-recommend to visitors e.g. families over half-term. Provide front line staff/vols with a list of activities across all three sites - possibility to give physical print outs to visitors to reference e.g. summer holiday events planner | All sites to hold regular team briefings with their staff/volunteers to keen them informed of upcoming activities and news - including across the three sites. Geoff, Karen and Janet to provide regular updates (or delegate to staff/volunteer) to enable cross-site sharing of information. | Geoff, Karen and Janet | Year One | Free. Time resource only Possible low on-site print costs of events print out
10 | Local event listings websites | Submit events to Visit Lincolnshire website when sending out PR stories in order to capture visitors to the Visit Lincolnshire sites as well as local media audiences. | Events are submitted via the email address: visit@lincs-chamber.co.uk | One individual to submit for all 3 sites (Karen, Geoff and Janet to determine) | Year Two | Free. Time resource only
11 | E-newsletter | Replace Moulton Windmill annual newsletter with a collaborative newsletter including information across all three sites. Published at least twice a year (once a month maximum) to remain relevant and seasonal. A minimum of one newsletter a year published in March would make sure the spring/summer holidays are covered. This newsletter could detail events, activities, news - including conservation work and general site news. This would be emailed out to a online mailing list - which visitors can sign up to on the website. This would save on the current postage and printing of the mill newsletter. Sites could have some physical copies available so previous recipients can come in and pick up a copy if preferred. Having a few copies available for visitors to read in the Moulton Mill Cafe would also be a nice touch - balanced with the table talkers so visitors are not bombarded or overwhelmed. Content can be re-used across the different elements, newsletter, table talker, social etc. via the Marketing & PR plan. | When discussing the build of your website, include in the brief that you would like a 'sign up to newsletter' function. They will also be able to take you through different options in terms of e-newsletter platforms such as MailChimp or CampaignMonitor that mean you can compile and send out your newsletters yourselves. It is worth considering the impact of the new data regulation (GDPR) coming in this May, and perhaps gaining some legal advice on how to retain legal data for your future use. | One individual to co-ordinate for all 3 sites (Karen, Geoff and Janet to determine) It could make sense for this individual to be the same individual co-ordinating the table talkers and PRs, as the information will be used for across these platforms. | Year One Included as part of the build of the website. It would be best to wait until all social media, website, and site programming activity is up and running smoothly before collecting new sign ups and sending out newsletters. | Lower cost of fewer physical print outs (maximum 10 for each site) Could be done on-site Saving on postage Cost of use of online e-newsletter platform = Campaign Monitor (used previously by NT consultant) Basic package is understood to be £9 per month to send 2,5000 emails across campaigns and automated emails. £29 per month for unlimited emails and unlimited proofs prior to sending out. With Campaign Monitor, you can always buy extra credits if needed for a particular campaign to cover yourself until the next batch.

## Yr 1
Marketing Planner Year one
Months |  | January | February | March | April | May | June | July | August | September | October | November | December
Tasks | Target audience
Create marketing plan | bar: March to April
Send out tender for web design and build | bar: April
Design brand and build website | bar: May to July
Create new collaborative Facebook (FB) and Twitter (Tw) pages | bar: July
Launch new website and communicate through FB & Tw | bar: August
Collaborative leaflet | bar: August to September
On site table talkers | bar: September
Briefing to visit reception staff | bar: July to August
Social media plan implementation | bar: August to December

## Yrs 2-3
Marketing Planner Years 2-3 |  | Please
Months |  | January | February | March | April | May | June | July | August | September | October | November | December
Key message/theme for the year | Please note the below are ideas only, actual detail will depend on programming, events and the stories that come from each place during the planning process
Tasks | Target audience
Website content | Families, independent adults, heritage enthusiasts | Please January: Add Feb half term activities; Please February: Share stories of the people behind the places (historic, present, volunteers); Please March: Refresh with spring and Easter content; Please April: Add May half-term events; Please May: Refresh with summer content and ensure all events up to date; Please September: Add Oct half-term and Christmas events (people start searching for Christmas during this month)
Facebook (this will depend on programming) | Families, independent adults, heritage enthusiasts
Twitter (this will depend on programming) | Local media, local interest groups, independent adults
Digital advertising (PPC (pay per click), Facebook) (this will depend on programming)
PR |  | Please January: Half-term PR; Please February: Volunteer recruitment PR to local media through use of current volunteer experiences; Please March: Easter PR Invite BBC Radio Lincs for feature - plug upcoming Spring and Summer activities; Please April: May half-term PR
Collaborative leaflet |  | Please January: Same basic visitor information; Please February: Same basic visitor information; Please March: Same basic visitor information; Please April: Same basic visitor information; Please May: Same basic visitor information
On site table talkers |  | Please January: Detail what events are coming up - half-term; Please March: Detail what events are coming up - Easter and Summer; Please April: Detail what events are coming up - Easter and Summer; Please May: Detail what events are coming up - Easter and Summer
Briefing to visit reception staff |  | Please January: Half-term activity across three sites; Please February: Spring and summer events across 3 sites; Please March: Spring and summer events across 3 sites; Please April: Spring and summer events across 3 sites; Please May: Spring and summer events across 3 sites
Posters/leaflets in local businesses |  | Please January: Half-term activity across three sites; Please February: Spring and summer events across 3 sites; Please March: Spring and summer events across 3 sites; Please April: Spring and summer events across 3 sites; Please May: Spring and summer events across 3 sites
Local event listings websites |  | Please January: Half-term activity across three sites; Please February: Spring and summer events across 3 sites; Please March: Spring and summer events across 3 sites; Please April: Spring and summer events across 3 sites; Please May: Spring and summer events across 3 sites

## Yrs 4-5
Marketing Planner Years 4-5
Months |  | January | February | March | April | May | June | July | August | September | October | November | December
Key message/theme for the year
Tasks | Target audience
Website content
Facebook
Twitter
Digital advertising (PPC (pay per click), Facebook)
PR
Collaborative leaflet
On site table talkers
Briefing to visit reception staff
Posters/leaflets in local businesses
Local event listings websites

## Social media plan
Social media plan
| Mon | Tues | Weds | Thurs | Fri | Sat | Sun
| Inspiring photos | Moulton Mill | Chain Bridge Forge | Pinchbeck Pump Engine | Cross promotion to inspire weekend visits
Each month we would recommend having a rough plan of the content you will be sharing (example below) and to spend a small amount of time each week scheduling content so you know messages are
being communicated, this then only requires a few minutes per day to reply to messages. We have found very few people respond to questions of calls to action on a Monday so sharing engaging and
inspiring images on Mondays is recommended.
On Twitter try linking in with hashtag conversations for example #lincshour, this is a great way to talk to your local community. And on both channels link in with celebratory days such a Lincolnshire Day
October
Mon | 1 | Lincolnshire day
Tues | 2
Weds | 3
Thurs | 4
Fri | 5 | World smile day
Sat | 6
Sun | 7
Mon | 8
Tues | 9
Weds | 10 | Woad festival starts in xxx days
Thurs | 11
Fri | 12
Sat | 13
Sun | 14
Mon | 15
Tues | 16 | National baking week starts - links with flour/mill/share a recipe
Weds | 17
Thurs | 18
Fri | 19
Sat | 20 | Share photos from Woad fest
Sun | 21 | Share photos from Woad fest
Mon | 22
Tues | 23
Weds | 24 | Be a blacksmith - share content on how to join in at CBF
Thurs | 25
Fri | 26
Sat | 27
Sun | 28
Mon | 29
Tues | 30
Weds | 31 | Happy Halloween